## Campaign Tracker
Contact ID | Organization | Category | Contact Email | Status | Initial Contact Date | Follow-up Date | Meeting Scheduled | Meeting Date | Response Type | Interest Level | Amount Interest | Notes
1 | ADIA | SWF - Tier 1 | contact@adia.ae | Ready to Contact |  |  | No
2 | Mubadala | SWF - Tier 1 | info@mubadala.com | Ready to Contact |  |  | No
4 | PIF | SWF - Tier 1 | Info@pif.gov.sa | Ready to Contact |  |  | No
6 | QIA | SWF - Tier 1 | media@qia.qa | Ready to Contact |  |  | No
7 | KIA | SWF - Tier 1 | information@kia.gov.kw | Ready to Contact |  |  | No
34 | DMCC | FO Hub | info@dmcc.ae | Ready to Contact |  |  | No |  |  |  |  | Network hub - 800+ members
35 | ADGM | FO Hub | connect@adgm.ae | Ready to Contact |  |  | No |  |  |  |  | Network hub - 300+ members
31 | Al Nahyan FOs | Royal FO | TBD | Research |  |  | No |  |  |  |  | Formal channels required
32 | Al Maktoum FOs | Royal FO | TBD | Research |  |  | No |  |  |  |  | Dubai government relations
22 | Fajr Capital | PE/Crypto - High Priority | contact@fajrcapital.ae | Ready to Contact |  |  | No |  |  |  |  | $50B+ sovereign PE
23 | Lunate | PE/Crypto - High Priority | contact@lunate.ae | Ready to Contact |  |  | No |  |  |  |  | $50B+ multi-strategy fund
24 | Klumi Ventures | Crypto - High Priority | contact@klumi.ae | Ready to Contact |  |  | No |  |  |  |  | Digital asset manager
25 | Cypher Capital | Crypto - High Priority | contact@cyphercapital.io | Ready to Contact |  |  | No |  |  |  |  | Blockchain VC

## Action Plan
Week | Phase | Target | Actions | Contacts | Expected Outcomes
Week | Phase | Target | Actions | Contacts | Expected Outcomes
Week 1 | Phase 1: Tier 1 SWFs | ADIA, Mubadala, PIF, QIA, KIA | Send formal intro emails to all 5 SWFs; Include executive summary | 5 emails | 20-30% response rate; 1-2 scheduling calls
Week 1-2 | Phase 2: Network Hubs | DMCC, ADGM | Contact DMCC investment committee; Contact ADGM fund management office; Request member briefing slots | 2 strategic emails | Positive response: ~80%; Committee meetings scheduled
Week 2 | Phase 3: New PE Funds | Fajr Capital, Lunate, Klumi, Cypher, Morningstar, CV VC, Ghaf Capital | Email outreach to all 7 crypto/PE funds; Emphasize Bitcoin mining infrastructure fit | 7 emails | 40-50% response rate; 3-4 meetings scheduled
Week 2-3 | Phase 3: Royal Family FOs | Al Nahyan, Al Maktoum, Saudi Royal | Research formal contact channels; Contact through government business offices; Formal institutional outreach | 3 formal introductions | Government office routing; 2-4 week response time
Week 3 | Phase 4: Emerging FOs | LinkedIn targeting + DMCC/ADGM residents | LinkedIn outreach to 50+ family office principals; Partner with FO advisory firms; Wealth mgmt firm outreach | 50-100 contacts | 15-25% response rate; 10-15 initial conversations
Week 4 | Phase 4: Secondary Funds | Waha Capital, Shuaa Capital, Gulf Capital | Email outreach to PE/FO-backed firms; Standard business development approach | 3 emails | 25-35% response rate; Follow-up calls scheduled
Week 4-5 | Follow-up & Relationship | All non-responsive Tier 1/2/3 | Send follow-up emails to non-respondents; Refine messaging based on response feedback | Varies | Second wave of responses; Meeting confirmations

## Critical Contacts Research
Research Priority | Organization | Contact Type | Research Needed | Deadline | Status
Research Priority | Organization | Contact Type | Research Needed | Deadline | Status
CRITICAL | Al Nahyan FOs | Abu Dhabi Investment Council Contact | Find investment council email/contact; Identify appropriate committee member | This Week | In Progress
CRITICAL | Al Maktoum FOs | Dubai Government Business Contact | Dubai government relations contact; Emaar/DP World connection | This Week | In Progress
CRITICAL | Saudi Royal FOs | PIF/NEOM/Ministry Contact | PIF contact for Family Office info; Saudi Ministry email | This Week | In Progress
HIGH | DMCC | Investment Committee Chair | DMCC investment committee chair name/contact; Committee meeting schedule | Week 1 | Pending
HIGH | ADGM | Fund Management Director | ADGM fund management office director; Briefing schedule | Week 1 | Pending
HIGH | Independent FOs | Family Office Network Lists | Dubai/GCC family office databases; Emerging FO contact lists | Week 2 | Pending
MEDIUM | FO Advisory Firms | Partnership Contacts | Family office advisory firms in UAE/GCC; Wealth management partners | Week 2 | Pending
MEDIUM | Crypto VCs | LinkedIn Profiles | Key contacts at Cypher, Morningstar, CV VC, Ghaf for relationship building | Week 2 | Pending

## Metrics Dashboard
OUTREACH CAMPAIGN METRICS
Metric | Target | Current | Progress
Total Contacts | 42 | 0 | 0%
Emails Sent | 42 | 0 | 0%
Responses Received | 15 | 0 | 0%
Response Rate | 35% | 0% | 0%
Meetings Scheduled | 10 | 0 | 0%
BY CATEGORY
SWFs Contacted | 7 | 0 | 0%
Infrastructure Funds | 8 | 0 | 0%
Crypto/Bitcoin Funds | 14 | 0 | 0%
Family Offices | 8 | 0 | 0%
Strategic Corporates | 5 | 0 | 0%
EXPECTED OUTCOMES
Phase 1 (Week 1-2) Response Rate | 30% | TBD | TBD
Phase 2 (Week 2-3) Response Rate | 80% | TBD | TBD
Phase 3 (Week 3-4) Response Rate | 45% | TBD | TBD
Phase 4 (Week 4+) Response Rate | 25% | TBD | TBD
PIPELINE VALUE (Est.)
High Priority Conversations | $2-5B | TBD | TBD
Medium Priority Conversations | $1-2B | TBD | TBD
Exploratory Discussions | $500M-1B | TBD | TBD
Total Pipeline Value | $3.5-8B+ | TBD | TBD